## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 14 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | hours
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Build Kinect interface | 6 | 5 | 9 | 7 | 60%
Learn Basic Sign Language Symbols | 1 | 2 | 2 | 1 | 100%
learn Matlab Machine Learning | 2 | 6 | 1 | 6 | 90%
impliement matlab machine learning | 8 | 14 | 8 | 14 | 0%
Teach Gestures | 21 | 3 | 21 | 3 | 0%
Test | 24 | 2 | 24 | 2 | 0%
Error Fixing | 25 | 4 | 25 | 4 | 0%
Poster | 27 | 4 | 27 | 4 | 0%
Report | 7 | 34 | 7 | 34 | 15%
Activity 10 | 0 | 0 | 0 | 0 | 0%
Activity 11 | 0 | 0 | 0 | 0 | 0%
Activity 12 | 0 | 0 | 0 | 0 | 0%
Activity 13 | 0 | 0 | 0 | 0 | 50%
Activity 14 | 0 | 0 | 0 | 0 | 0%
Activity 15 | 0 | 0 | 0 | 0 | 1%
Activity 16 | 0 | 0 | 0 | 0 | 80%
Activity 17 | 0 | 0 | 0 | 0 | 0%
Activity 18 | 0 | 0 | 0 | 0 | 0%
Activity 19 | 0 | 0 | 0 | 0 | 0%
Activity 20 | 0 | 0 | 0 | 0 | 0%
Activity 21 | 0 | 0 | 0 | 0 | 44%
Activity 22 | 0 | 0 | 0 | 0 | 0%
Activity 23 | 0 | 0 | 0 | 0 | 12%
Activity 24 | 0 | 0 | 0 | 0 | 5%
Activity 25 | 0 | 0 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 50%